## 00_Cover
HEAVY WAREHOUSE INTELLIGENCE
Project Control Book · CadetX Virtual Work Experience · Data Analytics & Data Science
Project | Heavy Supplier, Inventory & Warehouse Analytics
Repository | github.com/<org>/heavy-warehouse-intelligence
Duration | 12 weekly sprints · 14 Sep 2026 – 04 Dec 2026
Team | Eswar Mahalingam (Data Scientist) · Data Analyst 1 · Data Analyst 2
Dataset | 12 CSV tables · 605,141 rows · 6 branches · 30 SKUs · 8 suppliers · 500 customers · 2019–2024
Owner of this file | Weekly Scrum Master (rotating)
Version | v0.1 · 15 Sep 2026
Legend | Yellow cells / blue text = team inputs · black = formulas · navy header = do not edit
SHEET INDEX
01_Data_Dictionary | All 134 columns across 12 tables — type, nulls, unique, description, key role
02_Table_Profile | Row counts, nulls, duplicates, date coverage, file size per table
03_KPI_Framework | 41 KPIs — formula, source, grain, target, owner, dashboard, status
04_Sprint_Tracker | 12 sprints — goal, Scrum Master, tasks, status %, submission tag
05_Task_Catalogue | All 59 catalogue tasks — phase, week, owner, status, notebook, result
06_DQ_Issue_Log | Data-quality issues DQ-001… with severity, rule, owner, status
07_Team_Roster | Members, roles, contact, Scrum Master rotation, meeting cadence
08_Assumptions | Every hard-coded number used in analysis, with source
PROGRAMME STATUS
Sprints completed | 0 | of 12
Tasks done | 0 | of 59
Tasks in progress | 1
Open DQ issues | 5
KPIs live | 0 | of 41

## 01_Data_Dictionary
Data Dictionary
134 columns · 12 tables · source: data/raw/*.csv · descriptions from CadetX Fields Documentation (edit column I if needed)
# | Table | Column | Type | Non-null | Nulls | Unique | Example | Description | Key
1 | branches | branch_id | text | 6 | 0 | 6 | DEL001 | Primary key (e.g. DEL001) | PK
2 | branches | branch_name | text | 6 | 0 | 6 | Delhi Central | Branch display name
3 | branches | city | text | 6 | 0 | 6 | Delhi | City
4 | branches | state | text | 6 | 0 | 6 | Delhi | Indian state
5 | branches | region | text | 6 | 0 | 4 | North | North / South / East / West
6 | branches | warehouse_type | text | 6 | 0 | 4 | Central | Central · Regional · Branch · Service Hub
7 | branches | warehouse_capacity | text | 6 | 0 | 6 | 45230 sqft | Storage area as text '45230 sqft' → parse to int (sq ft)
8 | branches | service_center_available | text | 6 | 0 | 2 | Yes | Yes/No — on-site service centre
9 | branches | manager_id | int | 6 | 0 | 6 | 9593 | Branch manager employee id
10 | branches | total_employees | int | 6 | 0 | 6 | 92 | Headcount
11 | branches | avg_monthly_revenue | int | 6 | 0 | 6 | 5234890 | Average monthly revenue (₹)
12 | branches | monthly_operational_cost | int | 6 | 0 | 6 | 3189000 | Monthly operating cost (₹)
13 | branches | market_demand_index | int | 6 | 0 | 4 | 9 | Demand score 1–10 (10 = highest)
14 | products | product_id | text | 30 | 0 | 30 | P001 | Primary key (P001–P030) | PK
15 | products | product_name | text | 30 | 0 | 30 | Hydraulic Pump HP-300 | Part name + part code
16 | products | category | text | 30 | 0 | 15 | Hydraulic | Hydraulic, Filters, Engine, Undercarriage…
17 | products | machine_type | text | 30 | 0 | 6 | Excavator | Excavator, Loader, Bulldozer, Crane, Dumper, All
18 | products | brand | text | 30 | 0 | 6 | CAT | CAT, JCB, Komatsu, Volvo, Tata Hitachi, Generic
19 | products | model_compatibility | text | 30 | 0 | 18 | CAT 320D | Compatible machine model
20 | products | unit_cost | int | 30 | 0 | 30 | 18950 | Standard purchase cost (₹)
21 | products | unit_price | int | 30 | 0 | 28 | 24500 | List selling price (₹)
22 | products | margin_percentage | float | 30 | 0 | 30 | 29.2 | (price − cost) ÷ cost × 100
23 | products | gst_rate | int | 30 | 0 | 2 | 28 | GST % (18 or 28)
24 | products | weight_kg | float | 30 | 0 | 29 | 38.5 | Unit weight (kg) — drives space & freight
25 | products | dimensions_cm | text | 30 | 0 | 29 | 40x25x25 | L×W×H in cm
26 | products | material_type | text | 30 | 0 | 10 | steel | steel, rubber, alloy…
27 | products | warranty_months | int | 30 | 0 | 5 | 12 | Warranty period
28 | products | reorder_level | int | 30 | 0 | 20 | 15 | Master reorder point (units)
29 | products | safety_stock | int | 30 | 0 | 17 | 10 | Master safety stock (units)
30 | products | max_stock_level | int | 30 | 0 | 19 | 40 | Master max stock (units)
31 | products | lead_time_days | int | 30 | 0 | 19 | 21 | Standard replenishment lead time
32 | products | criticality_level | text | 30 | 0 | 3 | High | High / Medium / Low
33 | products | usage_frequency | text | 30 | 0 | 3 | Medium | High / Medium / Low
34 | products | uom | text | 30 | 0 | 3 | piece | piece, set, cartridge
35 | products | last_purchase_price | int | 30 | 0 | 30 | 18500 | Last PO unit price (₹)
36 | products | last_purchase_date | date | 30 | 0 | 30 | 2019-03-15 | Date of last purchase
37 | suppliers | supplier_id | text | 8 | 0 | 8 | SUP0001 | Primary key (SUP0001–SUP0008) | PK
38 | suppliers | supplier_name | text | 8 | 0 | 8 | Shenzhen OEM Supplies | Supplier name
39 | suppliers | supplier_type | text | 8 | 0 | 3 | OEM | OEM · Distributor · Local Vendor
40 | suppliers | product_category | text | 8 | 0 | 3 | Medium Parts | Small / Medium / Large Parts
41 | suppliers | city | text | 8 | 0 | 8 | Shenzhen | Supplier city (China)
42 | suppliers | province | text | 8 | 0 | 6 | Guangdong | Chinese province
43 | suppliers | region | text | 8 | 0 | 3 | South China | South / East / North China
44 | suppliers | pincode | int | 8 | 0 | 8 | 586808 | Postal code (synthetic, Indian format)
45 | suppliers | lead_time_days | int | 8 | 0 | 7 | 19 | Contracted lead time
46 | suppliers | reliability_score | int | 8 | 0 | 3 | 5 | 1–5 (5 = best)
47 | suppliers | import_duty_rate | int | 8 | 0 | 4 | 8 | Import duty % applied to landed cost
48 | suppliers | china_tax_id | text | 8 | 0 | 8 | 90SUZHOU398241 | Supplier tax identifier
49 | customers | customer_id | text | 500 | 0 | 500 | C0001 | Primary key (C0001–C0500) | PK
50 | customers | customer_type | text | 500 | 0 | 5 | Retail | Government · Corporate · Dealer · Fleet Owner · Retail
51 | customers | industry_segment | text | 500 | 0 | 6 | Construction | Mining, Logistics, Construction, Infrastructure, Manufacturing, Rental
52 | customers | city | text | 500 | 0 | 21 | Kolkata | City
53 | customers | state | text | 500 | 0 | 16 | West Bengal | State
54 | customers | pincode | int | 500 | 0 | 500 | 991035 | Postal code
55 | customers | region | text | 500 | 0 | 6 | East | North / South / East / West
56 | customers | branch_id | text | 500 | 0 | 6 | KOL001 | FK → branches (home branch) | FK
57 | customers | credit_limit | int | 500 | 0 | 500 | 45896 | Approved credit limit (₹)
58 | customers | current_balance | int | 500 | 0 | 499 | 43284 | Outstanding receivable (₹)
59 | customers | payment_terms | text | 500 | 0 | 5 | Advance | Advance · Net 15/30/45/60
60 | customers | customer_since | text | 500 | 0 | 467 | 2024-04-10 | Onboarding date
61 | customers | last_purchase_date | date | 500 | 0 | 449 | 2024-04-25 | Most recent order date
62 | customers | total_purchase_value | int | 500 | 0 | 500 | 3892818 | Lifetime purchase value (₹)
63 | customers | customer_rating | int | 500 | 0 | 5 | 4 | Internal rating 1–5
64 | inventory_master | product_id | text | 180 | 0 | 30 | P001 | FK → products | FK
65 | inventory_master | branch_id | text | 180 | 0 | 6 | DEL001 | FK → branches | FK
66 | inventory_master | opening_stock | int | 180 | 0 | 127 | 196 | Stock at period start (units)
67 | inventory_master | reorder_level | int | 180 | 0 | 75 | 59 | Branch-level reorder point
68 | inventory_master | safety_stock | int | 180 | 0 | 63 | 46 | Branch-level safety stock
69 | inventory_master | max_stock | int | 180 | 0 | 148 | 340 | Branch-level max stock
70 | inventory_master | current_stock | int | 180 | 0 | 180 | 115928 | Current on-hand — ⚠ values ~100k vs max ~500: reconcile with ledger
71 | inventory_master | warehouse_bin | text | 180 | 0 | 95 | C15 | Bin location (e.g. C15)
72 | purchase_orders_header | po_id | text | 24000 | 0 | 24000 | PO-141186 | Primary key | PK
73 | purchase_orders_header | supplier_id | text | 24000 | 0 | 8 | SUP0001 | FK → suppliers | FK
74 | purchase_orders_header | branch_id | text | 24000 | 0 | 6 | PUN001 | FK → branches (receiving site) | FK
75 | purchase_orders_header | order_date | date | 24000 | 0 | 2192 | 2019-04-10 | PO raised date
76 | purchase_orders_header | expected_delivery_date | date | 24000 | 0 | 2207 | 2019-04-29 | Promised delivery
77 | purchase_orders_header | received_date | date | 21630 | 2370 | 2207 | 2019-04-29 | Actual receipt — NULL for Cancelled POs
78 | purchase_orders_header | po_status | text | 24000 | 0 | 2 | Received | Received · Cancelled
79 | purchase_orders_header | total_cost | float | 24000 | 0 | 24000 | 22955232.11 | Sum of line totals ex-GST (₹)
80 | purchase_orders_header | total_gst_amount | float | 24000 | 0 | 24000 | 6427464.990800001 | GST (₹)
81 | purchase_orders_header | grand_total | float | 24000 | 0 | 24000 | 29382697.1008 | Incl. GST (₹)
82 | purchase_orders_lines | po_id | text | 155495 | 0 | 24000 | PO-141186 | FK → purchase_orders_header | FK
83 | purchase_orders_lines | line_number | int | 155495 | 0 | 12 | 1 | Line sequence within PO
84 | purchase_orders_lines | product_id | text | 155495 | 0 | 30 | P004 | FK → products | FK
85 | purchase_orders_lines | quantity | int | 155495 | 0 | 281 | 234 | Units ordered
86 | purchase_orders_lines | unit_cost | float | 155495 | 0 | 142292 | 34709.54 | Negotiated unit cost (₹)
87 | purchase_orders_lines | gst_rate | int | 155495 | 0 | 2 | 28 | GST %
88 | purchase_orders_lines | line_total | float | 155495 | 0 | 155224 | 8122032.36 | qty × unit_cost
89 | purchase_orders_lines | gst_amount | float | 155495 | 0 | 155254 | 2274169.0608 | line_total × gst_rate
90 | purchase_orders_lines | line_grand_total | float | 155495 | 0 | 155269 | 10396201.4208 | line_total + gst
91 | sales_orders_header | so_id | text | 20000 | 0 | 20000 | SO-990591 | Primary key | PK
92 | sales_orders_header | customer_id | text | 20000 | 0 | 500 | C0070 | FK → customers | FK
93 | sales_orders_header | branch_id | text | 20000 | 0 | 6 | AHM001 | FK → branches (fulfilling site) | FK
94 | sales_orders_header | order_date | date | 20000 | 0 | 2192 | 2022-05-24 | Order date
95 | sales_orders_header | delivery_date | date | 20000 | 0 | 2204 | 2022-05-28 | Delivery date
96 | sales_orders_header | order_status | text | 20000 | 0 | 2 | Delivered | Delivered · Cancelled
97 | sales_orders_header | payment_terms | text | 20000 | 0 | 5 | Net 30 | Advance · Net 15/30/45/60
98 | sales_orders_header | total_order_value | int | 20000 | 0 | 17905 | 1345720 | Ex-GST (₹)
99 | sales_orders_header | total_gst_amount | float | 20000 | 0 | 18749 | 374439.6 | GST (₹)
100 | sales_orders_header | grand_total | float | 20000 | 0 | 18735 | 1720159.6 | Incl. GST (₹)
101 | sales_orders_header | sales_channel | text | 20000 | 0 | 4 | Counter Sale | Field Sales · Dealer Network · Counter Sale · Online
102 | sales_orders_lines | so_id | text | 130402 | 0 | 20000 | SO-990591 | FK → sales_orders_header | FK
103 | sales_orders_lines | line_number | int | 130402 | 0 | 12 | 1 | Line sequence
104 | sales_orders_lines | product_id | text | 130402 | 0 | 30 | P018 | FK → products | FK
105 | sales_orders_lines | quantity | int | 130402 | 0 | 20 | 19 | Units sold
106 | sales_orders_lines | unit_price | int | 130402 | 0 | 28 | 11300 | Selling price (₹)
107 | sales_orders_lines | gst_rate | int | 130402 | 0 | 2 | 28 | GST %
108 | sales_orders_lines | line_total | int | 130402 | 0 | 534 | 214700 | qty × unit_price
109 | sales_orders_lines | gst_amount | float | 130402 | 0 | 534 | 60116.00000000001 | GST (₹)
110 | sales_orders_lines | line_grand_total | float | 130402 | 0 | 534 | 274816.0 | Incl. GST (₹)
111 | invoices | invoice_id | text | 18033 | 0 | 17836 | INV-325361 | Primary key | PK
112 | invoices | so_id | text | 18033 | 0 | 18033 | SO-990591 | FK → sales_orders_header | FK
113 | invoices | customer_id | text | 18033 | 0 | 500 | C0070 | FK → customers | FK
114 | invoices | branch_id | text | 18033 | 0 | 6 | AHM001 | FK → branches | FK
115 | invoices | invoice_date | date | 18033 | 0 | 2203 | 2022-05-28 | Invoice date
116 | invoices | due_date | date | 18033 | 0 | 2235 | 2022-06-27 | Payment due date
117 | invoices | total_order_value | int | 18033 | 0 | 16248 | 1345720 | Ex-GST (₹)
118 | invoices | total_gst_amount | float | 18033 | 0 | 16951 | 374439.6 | GST (₹)
119 | invoices | grand_total | float | 18033 | 0 | 16938 | 1720159.6 | Incl. GST (₹)
120 | invoices | payment_status | text | 18033 | 0 | 3 | Unpaid | Paid · Partially Paid · Unpaid
121 | payments | payment_id | text | 19257 | 0 | 19055 | PAY-207775 | Primary key | PK
122 | payments | invoice_id | text | 19257 | 0 | 16036 | INV-786913 | FK → invoices | FK
123 | payments | payment_date | date | 19257 | 0 | 2243 | 2023-10-07 | Payment date
124 | payments | payment_amount | float | 19257 | 0 | 18778 | 3354624.0 | Amount received (₹)
125 | payments | payment_method | text | 19257 | 0 | 5 | Cheque | UPI · Credit Card · Bank Transfer · Cheque · Cash
126 | stock_ledger | movement_id | text | 237230 | 0 | 237230 | MOV-OUT-184742 | Primary key | PK
127 | stock_ledger | product_id | text | 237230 | 0 | 30 | P001 | FK → products | FK
128 | stock_ledger | branch_id | text | 237230 | 0 | 6 | AHM001 | FK → branches | FK
129 | stock_ledger | movement_type | text | 237230 | 0 | 3 | OUT | IN (PO receipt) · OUT (SO despatch) · ADJUSTMENT
130 | stock_ledger | movement_date | date | 237230 | 0 | 2218 | 2019-01-03 | Movement date
131 | stock_ledger | quantity | int | 237230 | 0 | 300 | 8 | Units moved
132 | stock_ledger | reference_type | text | 237230 | 0 | 3 | SO | PO · SO · ADJ
133 | stock_ledger | reference_id | text | 237230 | 0 | 43709 | SO-157767 | FK → PO / SO id | FK
134 | stock_ledger | running_balance | int | 237230 | 0 | 98171 | 228 | Balance after movement

## 02_Table_Profile
Table Profile
Row-level profile of every raw table (Week-1 baseline) — re-run notebooks/01_data_profiling.ipynb to refresh
Table | Grain / description | Rows | Cols | Nulls | Dup rows | Date coverage | Size (MB) | Null %
branches | Warehouse / branch master — one row per physical site | 6 | 13 | 0 | 0 |  | 0 | 0%
products | Product / SKU master — heavy-machinery spare parts | 30 | 23 | 0 | 0 | last_purchase_date: 2019-03-15 → 2025-04-27 | 0 | 0%
suppliers | Supplier master — 8 China-based OEM / distributor / local vendors | 8 | 12 | 0 | 0 |  | 0 | 0%
customers | Customer master — 500 B2B accounts | 500 | 15 | 0 | 0 | last_purchase_date: 2015-04-30 → 2024-12-27 | 0.06 | 0%
inventory_master | Stock position per product × branch (30 × 6 = 180 rows) | 180 | 8 | 0 | 0 |  | 0.01 | 0%
purchase_orders_header | Purchase order header — one row per PO to a supplier | 24000 | 10 | 2370 | 0 | order_date: 2019-01-01 → 2024-12-31; expected_delivery_date: 2019-01-11 → 2025-01-28; received_date: 2019-01-11 → 2025-01-28 | 2.65 | 0.9875%
purchase_orders_lines | Purchase order line items | 155495 | 9 | 0 | 0 |  | 11.39 | 0%
sales_orders_header | Sales order header — one row per customer order | 20000 | 11 | 0 | 0 | order_date: 2019-01-01 → 2024-12-31; delivery_date: 2019-01-02 → 2025-01-13 | 2.11 | 0%
sales_orders_lines | Sales order line items | 130402 | 9 | 0 | 0 |  | 7.19 | 0%
invoices | Invoices — one per delivered sales order | 18033 | 10 | 0 | 0 | invoice_date: 2019-01-03 → 2025-01-13; due_date: 2019-01-20 → 2025-03-14 | 1.69 | 0%
payments | Payments received against invoices | 19257 | 5 | 0 | 0 | payment_date: 2019-01-09 → 2025-03-20 | 0.98 | 0%
stock_ledger | Stock movement ledger — every IN / OUT / ADJUSTMENT per product × branch | 237230 | 9 | 0 | 0 | movement_date: 2019-01-01 → 2025-01-28 | 14.88 | 0%
TOTAL |  | 605141 | 134 | 2370 | 0 |  | 40.96 | 0.04345%

## 03_KPI_Framework
KPI Framework
41 KPIs · edit Status (J) and Baseline (K) as each KPI goes live · mirrors docs/02_kpi_framework.md
ID | Domain | KPI | Formula | Source tables | Grain | Target | Owner | Dashboard | Status | Baseline value
INV-01 | Inventory | Inventory Turnover | Σ(OUT qty × unit_cost) ÷ avg(running_balance × unit_cost) | stock_ledger, products | product × branch × year | ≥ 4× | DA1 | Inventory Health | Planned
INV-02 | Inventory | Days Inventory Outstanding | 365 ÷ INV-01 | derived | product × branch | ≤ 90 days | DA1 | Inventory Health | Planned
INV-03 | Inventory | Stockout Rate | days with running_balance ≤ 0 ÷ total days | stock_ledger | product × branch | ≤ 2 % | DS | Inventory Health | Planned
INV-04 | Inventory | Overstock % | SKU-branch pairs with balance > max_stock ÷ 180 | stock_ledger, inventory_master | branch | ≤ 10 % | DA1 | Inventory Health | Planned
INV-05 | Inventory | Understock % | pairs with balance < reorder_level ÷ 180 | stock_ledger, inventory_master | branch | ≤ 5 % | DA1 | Inventory Health | Planned
INV-06 | Inventory | Inventory Ageing (days) | today − date of last OUT movement | stock_ledger | product × branch | ≤ 120 | DA1 | Inventory Health | Planned
INV-07 | Inventory | Dead-stock value | Σ balance × unit_cost where no OUT in 180 d | stock_ledger, products | branch | ↓ 30 % | DA1 | Inventory Health | Planned
INV-08 | Inventory | ABC class | cumulative revenue share: A ≤ 80 %, B ≤ 95 %, C rest | sales_orders_lines, products | product | — | DA1 | Product Performance | Planned
INV-09 | Inventory | Capital locked in stock | Σ running_balance × unit_cost (latest) | stock_ledger, products | branch | ↓ 15 % | DA1 | Inventory Health | Planned
PRD-01 | Product | Revenue contribution | Σ line_total ÷ total revenue | sales_orders_lines | product | — | DA1 | Product Performance | Planned
PRD-02 | Product | Gross margin % | Σ(qty × (unit_price − unit_cost)) ÷ Σ line_total | sales_orders_lines, products | product | ≥ 30 % | DA1 | Product Performance | Planned
PRD-03 | Product | Velocity (units/month) | Σ OUT qty ÷ months active | stock_ledger | product × branch | — | DA1 | Product Performance | Planned
PRD-04 | Product | Fast / slow mover flag | velocity quartile: Q4 fast, Q1 slow | derived | product | — | DA1 | Product Performance | Planned
PRD-05 | Product | Demand trend (YoY %) | (units yr n − yr n-1) ÷ yr n-1 | sales_orders_lines | product × year | — | DS | Product Performance | Planned
WH-01 | Warehouse | Throughput / day | Σ(IN + OUT qty) ÷ operating days | stock_ledger | branch | ↑ | DA1 | Warehouse Efficiency | Planned
WH-02 | Warehouse | Revenue per sq ft | avg_monthly_revenue ÷ capacity_sqft | branches | branch | ≥ ₹110 | DA1 | Warehouse Efficiency | Planned
WH-03 | Warehouse | Revenue per employee | avg_monthly_revenue ÷ total_employees | branches | branch | ≥ ₹55k | DA1 | Warehouse Efficiency | Planned
WH-04 | Warehouse | Operating margin % | (revenue − op cost) ÷ revenue | branches | branch | ≥ 35 % | DA1 | Warehouse Efficiency | Planned
WH-05 | Warehouse | Space utilisation % | Σ(balance × unit volume) ÷ capacity volume | stock_ledger, products, branches | branch | 65–85 % | DA1 | Warehouse Efficiency | Planned
WH-06 | Warehouse | Order-to-delivery days | delivery_date − order_date | sales_orders_header | branch | ≤ 5 | DA1 | Warehouse Efficiency | Planned
WH-07 | Warehouse | Warehouse Performance Score | weighted z-score of WH-01…06 | derived | branch | rank | DA1 | Warehouse Efficiency | Planned
SUP-01 | Supplier | On-time delivery % | received_date ≤ expected_delivery_date ÷ received POs | purchase_orders_header | supplier | ≥ 90 % | DA2 | Supplier Performance | Planned
SUP-02 | Supplier | Actual lead time (days) | received_date − order_date | purchase_orders_header | supplier | ≤ contracted | DA2 | Supplier Performance | Planned
SUP-03 | Supplier | Lead-time variance | σ(actual − contracted lead time) | purchase_orders_header, suppliers | supplier | ≤ 3 d | DA2 | Supplier Performance | Planned
SUP-04 | Supplier | Cancellation rate | Cancelled ÷ total POs | purchase_orders_header | supplier | ≤ 5 % | DA2 | Supplier Performance | Planned
SUP-05 | Supplier | Spend share | Σ grand_total ÷ total spend | purchase_orders_header | supplier | no supplier > 35 % | DA2 | Supplier Performance | Planned
SUP-06 | Supplier | Dependency risk (HHI) | Σ(spend share²) per product | purchase_orders_lines, header | product | < 0.25 | DA2 | Supplier Performance | Planned
SUP-07 | Supplier | Landed cost index | unit_cost × (1 + import_duty_rate) ÷ list unit_cost | PO lines, suppliers, products | supplier × product | — | DA2 | Supplier Performance | Planned
CUS-01 | Customer | RFM score | quintiles of recency, frequency, monetary | invoices | customer | — | DA2 | Customer Analytics | Planned
CUS-02 | Customer | CLV (historic) | Σ grand_total × margin % | invoices, products | customer | — | DA2 | Customer Analytics | Planned
CUS-03 | Customer | Retention rate | customers active in yr n and yr n-1 ÷ active yr n-1 | sales_orders_header | year | ≥ 80 % | DA2 | Customer Analytics | Planned
CUS-04 | Customer | Churn flag | no order in > 180 days | sales_orders_header | customer | ≤ 15 % | DS | Customer Analytics | Planned
CUS-05 | Customer | DSO | avg(payment_date − invoice_date) | invoices, payments | customer / branch | ≤ 45 d | DA2 | Customer Analytics | Planned
CUS-06 | Customer | Collection rate | Σ payment_amount ÷ Σ invoice grand_total | invoices, payments | branch | ≥ 95 % | DA2 | Customer Analytics | Planned
CUS-07 | Customer | Credit utilisation | current_balance ÷ credit_limit | customers | customer | ≤ 80 % | DA2 | Customer Analytics | Planned
FC-02 | Forecast | Reorder point | avg daily demand × lead time + safety stock | derived | product × branch | — | DS | Inventory Health | Planned
FC-03 | Forecast | Safety stock | z × σ_demand × √lead_time (z = 1.65 @ 95 %) | derived | product × branch | — | DS | Inventory Health | Planned
FC-04 | Forecast | Stockout risk probability | classifier P(balance ≤ 0 in next 30 d) | model output | product × branch | — | DS | Inventory Health | Planned
RSK-01 | Risk | Ledger reconciliation gap | inventory_master.current_stock − last running_balance | inventory_master, stock_ledger | product × branch | 0 | DS | Anomaly Monitor | Planned
RSK-02 | Risk | Adjustment rate | ADJUSTMENT qty ÷ total movement qty | stock_ledger | branch | ≤ 1 % | DS | Anomaly Monitor | Planned
RSK-03 | Risk | Movement anomaly count | Isolation-Forest / z-score > 3 on daily qty | stock_ledger | branch | ↓ | DS | Anomaly Monitor | Planned

## 04_Sprint_Tracker
Sprint Tracker
One row per sprint · Scrum Master updates Status, Portal-submitted and Notes every Friday · task counts pull from 05_Task_Catalogue
Week | Start | End | Phase | Sprint goal | Scrum Master | Status | Tasks done | Tasks planned | Done % | Git tag | Portal submitted | Notes / blockers
01 | 14-Sep | 18-Sep | Foundation | Profile all tables, propose KPIs, set up repo & control book | Eswar | In progress | 0 | 1 | 0% | vWeek-01 | ☐
02 | 21-Sep | 25-Sep | Foundation | Cleaning rules + star schema + data dictionary v1 | DA1 | Planned | 0 | 3 | 0% | vWeek-02 | ☐
03 | 28-Sep | 02-Oct | Foundation | Feature engineering + validation suite + first KPI pack | DA2 | Planned | 0 | 2 | 0% | vWeek-03 | ☐
04 | 05-Oct | 09-Oct | Product & Inventory | Product performance, ABC/Pareto, fast/slow movers | Eswar | Planned | 0 | 4 | 0% | vWeek-04 | ☐
05 | 12-Oct | 16-Oct | Product & Inventory | Turnover, stock health, ageing, over/understock | DA1 | Planned | 0 | 5 | 0% | vWeek-05 | ☐
06 | 19-Oct | 23-Oct | Warehouse | Space utilisation, throughput, capacity, performance score | DA2 | Planned | 0 | 7 | 0% | vWeek-06 | ☐
07 | 26-Oct | 30-Oct | Supplier | Contribution, reliability, dependency, critical suppliers | Eswar | Planned | 0 | 6 | 0% | vWeek-07 | ☐
08 | 02-Nov | 06-Nov | Customer | RFM, segmentation, CLV, retention, churn, cohorts | DA1 | Planned | 0 | 9 | 0% | vWeek-08 | ☐
09 | 09-Nov | 13-Nov | Predictive | Demand forecast, stockout risk, ROP, safety stock, scenarios | DA2 | Planned | 0 | 6 | 0% | vWeek-09 | ☐
10 | 16-Nov | 20-Nov | BI | 5 dashboards + KPI framework design | Eswar | Planned | 0 | 6 | 0% | vWeek-10 | ☐
11 | 23-Nov | 27-Nov | Risk & Strategy | Anomaly detection, shrinkage, strategy recommendations | DA1 | Planned | 0 | 8 | 0% | vWeek-11 | ☐
12 | 30-Nov | 04-Dec | Final | Consolidation, README portfolio, final presentation | DA2 | Planned | 0 | 2 | 0% | vWeek-12 | ☐

## 05_Task_Catalogue
Task Catalogue
59 tasks from the CadetX catalogue · pick, assign, track · Status feeds 04_Sprint_Tracker and 00_Cover
ID | Group | Task | Week | Phase | Owner | Status | Notebook / file | Key result (number + so-what) | Output link
A1 | Data Foundation & Preparation | Data Profiling & Structure Analysis | 1 | 1 Foundation | Eswar | In progress | notebooks/01_a1_data_profiling_structure_analy.ipynb
A2 | Data Foundation & Preparation | Data Cleaning & Quality Improvement | 2 | 1 Foundation | DA1 | Planned | notebooks/02_a2_data_cleaning_quality_improvem.ipynb
A3 | Data Foundation & Preparation | Data Integration & Dataset Merging | 2 | 1 Foundation | DA1 | Planned | notebooks/02_a3_data_integration_dataset_mergi.ipynb
A4 | Data Foundation & Preparation | Feature Engineering for Analytics | 3 | 1 Foundation | DA2 | Planned | notebooks/03_a4_feature_engineering_for_analyt.ipynb
A5 | Data Foundation & Preparation | Data Validation & Consistency Checks | 3 | 1 Foundation | DA2 | Planned | notebooks/03_a5_data_validation_consistency_ch.ipynb
A6 | Data Foundation & Preparation | Data Dictionary & Documentation | 2 | 1 Foundation | DA1 | Planned | notebooks/02_a6_data_dictionary_documentation.ipynb
B1 | Product & Inventory Analytics | Product Performance Analysis | 4 | 2 Analytics | DA1 | Backlog
B2 | Product & Inventory Analytics | Fast-Moving Product Identification | 4 | 2 Analytics | DA1 | Backlog
B3 | Product & Inventory Analytics | Slow-Moving & Dead Stock Identification | 4 | 2 Analytics | DA1 | Backlog
B4 | Product & Inventory Analytics | Inventory Turnover Analysis | 5 | 2 Analytics | DA1 | Backlog
B5 | Product & Inventory Analytics | Stock Health Assessment | 5 | 2 Analytics | DA1 | Backlog
B6 | Product & Inventory Analytics | Inventory Aging Analysis | 5 | 2 Analytics | DA2 | Backlog
B7 | Product & Inventory Analytics | ABC / Pareto Product Classification | 4 | 2 Analytics | Eswar | Backlog
B8 | Product & Inventory Analytics | Overstock & Understock Detection | 5 | 2 Analytics | DA2 | Backlog
B9 | Product & Inventory Analytics | Product Demand Trend Analysis | 5 | 2 Analytics | Eswar | Backlog
C1 | Warehouse Operations & Efficiency | Warehouse Space Utilisation Analysis | 6 | 2 Analytics | DA1 | Backlog
C2 | Warehouse Operations & Efficiency | Warehouse Throughput Analysis | 6 | 2 Analytics | DA1 | Backlog
C3 | Warehouse Operations & Efficiency | Warehouse Capacity Analysis | 6 | 2 Analytics | DA2 | Backlog
C4 | Warehouse Operations & Efficiency | Product–Warehouse Alignment | 6 | 2 Analytics | Eswar | Backlog
C5 | Warehouse Operations & Efficiency | Warehouse Performance Scoring | 6 | 2 Analytics | DA2 | Backlog
C6 | Warehouse Operations & Efficiency | Operational Bottleneck Detection | 6 | 2 Analytics | Eswar | Backlog
C7 | Warehouse Operations & Efficiency | Warehouse Utilisation Benchmarking | 6 | 2 Analytics | DA1 | Backlog
D1 | Supplier & Procurement Analytics | Supplier Contribution Analysis | 7 | 3 Predictive | DA2 | Backlog
D2 | Supplier & Procurement Analytics | Supplier Reliability Analysis | 7 | 3 Predictive | DA2 | Backlog
D3 | Supplier & Procurement Analytics | Supplier Performance Comparison | 7 | 3 Predictive | DA2 | Backlog
D4 | Supplier & Procurement Analytics | Supplier Dependency Risk Analysis | 7 | 3 Predictive | Eswar | Backlog
D5 | Supplier & Procurement Analytics | Critical Supplier Identification | 7 | 3 Predictive | Eswar | Backlog
D6 | Supplier & Procurement Analytics | Supplier Diversification Analysis | 7 | 3 Predictive | DA1 | Backlog
E1 | Customer Analytics | Customer Purchase Behaviour Analysis | 8 | 3 Predictive | DA2 | Backlog
E2 | Customer Analytics | RFM (Recency, Frequency, Monetary) Analysis | 8 | 3 Predictive | DA2 | Backlog
E3 | Customer Analytics | Customer Segmentation & Personas | 8 | 3 Predictive | Eswar | Backlog
E4 | Customer Analytics | Customer Lifetime Value (CLV) Estimation | 8 | 3 Predictive | DA2 | Backlog
E5 | Customer Analytics | Customer Retention Analysis | 8 | 3 Predictive | DA1 | Backlog
E6 | Customer Analytics | Customer Churn Analysis | 8 | 3 Predictive | Eswar | Backlog
E7 | Customer Analytics | Customer Cohort Analysis | 8 | 3 Predictive | DA1 | Backlog
E8 | Customer Analytics | High-Value Customer Identification | 8 | 3 Predictive | DA2 | Backlog
E9 | Customer Analytics | At-Risk Customer Identification | 8 | 3 Predictive | Eswar | Backlog
F1 | Forecasting & Predictive Analytics | Product Demand Forecasting | 9 | 3 Predictive | Eswar | Backlog
F2 | Forecasting & Predictive Analytics | Inventory Level Forecasting | 9 | 3 Predictive | Eswar | Backlog
F3 | Forecasting & Predictive Analytics | Stockout Risk Prediction | 9 | 3 Predictive | Eswar | Backlog
F4 | Forecasting & Predictive Analytics | Reorder Point Optimisation | 9 | 3 Predictive | DA1 | Backlog
F5 | Forecasting & Predictive Analytics | Safety Stock Calculation | 9 | 3 Predictive | DA1 | Backlog
F6 | Forecasting & Predictive Analytics | Scenario-Based Inventory Forecasting | 9 | 3 Predictive | DA2 | Backlog
G1 | Risk, Anomaly & Control Analytics | Inventory Movement Anomaly Detection | 11 | 4 BI & Strategy | Eswar | Backlog
G2 | Risk, Anomaly & Control Analytics | Stock Shrinkage Detection | 11 | 4 BI & Strategy | DA1 | Backlog
G3 | Risk, Anomaly & Control Analytics | Operational Risk Monitoring | 11 | 4 BI & Strategy | DA2 | Backlog
G4 | Risk, Anomaly & Control Analytics | Data Integrity & Error Detection | 11 | 4 BI & Strategy | DA1 | Backlog
H1 | Business Intelligence & Visualisation | Product Performance Dashboards | 10 | 4 BI & Strategy | DA1 | Backlog
H2 | Business Intelligence & Visualisation | Inventory Health Dashboards | 10 | 4 BI & Strategy | DA1 | Backlog
H3 | Business Intelligence & Visualisation | Warehouse Efficiency Dashboards | 10 | 4 BI & Strategy | DA2 | Backlog
H4 | Business Intelligence & Visualisation | Supplier Performance Dashboards | 10 | 4 BI & Strategy | DA2 | Backlog
H5 | Business Intelligence & Visualisation | Customer Analytics Dashboards | 10 | 4 BI & Strategy | DA2 | Backlog
H6 | Business Intelligence & Visualisation | KPI Framework Design | 10 | 4 BI & Strategy | Eswar | Backlog
I1 | Insight & Strategy Development | Inventory Optimisation Strategy | 11 | 4 BI & Strategy | Eswar | Backlog
I2 | Insight & Strategy Development | Warehouse Improvement Strategy | 11 | 4 BI & Strategy | DA1 | Backlog
I3 | Insight & Strategy Development | Supplier Strategy Recommendations | 11 | 4 BI & Strategy | DA2 | Backlog
I4 | Insight & Strategy Development | Customer Retention Strategy | 11 | 4 BI & Strategy | DA2 | Backlog
I5 | Insight & Strategy Development | Cost Reduction Opportunity Analysis | 12 | 4 BI & Strategy | Eswar | Backlog
I6 | Insight & Strategy Development | Operational Efficiency Improvement Plan | 12 | 4 BI & Strategy | DA1 | Backlog
Summary by status
| Backlog | 53
| Planned | 5
| In progress | 1
| Review | 0
| Done | 0
| Completion % | 0%

## 06_DQ_Issue_Log
Data Quality Issue Log
Log every issue found; never edit raw CSVs — fix in src/hwi/clean.py and reference the rule here
ID | Table.column | Issue | Severity | Rule / fix | Owner | Raised | Status | Resolved / notes
DQ-001 | purchase_orders_header.received_date | 2,370 nulls | Low | Keep null; exclude Cancelled from lead-time KPIs | DA1 | 15-Sep-26 | Accepted
DQ-002 | inventory_master.current_stock | ~100k units vs max_stock ≤ 582 | High | Recompute from ledger; flag as reconciliation gap RSK-01 | DS | 15-Sep-26 | Open
DQ-003 | branches.warehouse_capacity | Text with unit | Low | `str.replace(' sqft','').astype(int)` | DA1 | 15-Sep-26 | Open
DQ-004 | suppliers.pincode | 6-digit Indian format on Chinese addresses | Info | Do not geocode | DA2 | 15-Sep-26 | Accepted
DQ-005 | *.gst_amount / grand_total | Floating-point tails (e.g. 60116.00000000001) | Low | `round(2)` on load | DA1 | 15-Sep-26 | Open
DQ-006 | purchase_orders_header.grand_total | PO spend (₹44,169 Cr) ≫ sales (₹3,242 Cr) | High | Check PO qty scale vs SO; possible synthetic inflation — document, don't "fix" | DS | 15-Sep-26 | Open
DQ-007 | stock_ledger.running_balance | Verify balance(t) = balance(t-1) ± qty per product×branch | Medium | Continuity test in `clean.py` | DS | 15-Sep-26 | Open
DQ-008 | customers.last_purchase_date | Min 2015-04-30 predates ledger (2019) | Low | Keep; flag pre-2019 as legacy | DA2 | 15-Sep-26 | Accepted
DQ-009 | products.lead_time_days vs suppliers.lead_time_days | Two lead-time sources | Info | Use PO actuals; masters as reference | DA2 | 15-Sep-26 | Accepted
| Open issues: | 5
| High severity open: | 2

## 07_Team_Roster
Team Roster & Cadence
Team of 3 · Scrum Master rotates weekly · fill teammate details
Name | Role | Email | Phone | GitHub | Responsibilities | Scrum Master weeks
Eswar Mahalingam | Data Scientist | eswarmba05313@gmail.com | +91-9360548243 | @<handle> | Forecasting, stockout risk, ROP/safety stock, anomaly detection, KPI design | Weeks 1, 4, 7, 10
<Teammate 1> | Data Analyst 1 |  |  | @<handle> | Profiling, cleaning, product/inventory/warehouse KPIs, Power BI | Weeks 2, 5, 8, 11
<Teammate 2> | Data Analyst 2 |  |  | @<handle> | Supplier & customer analytics, RFM/CLV/churn, insight reports | Weeks 3, 6, 9, 12
Meeting cadence
Monday | Sprint planning | 30 min · agree goal, pick tasks, fill 05_Task_Catalogue
Wednesday | Stand-up | 15 min · done / doing / blocked → SPRINT_NOTES.md
Friday | Review + retro + submission | 30 min · demo results, update tracker, tag vWeek-XX, submit link to CadetX portal

## 08_Assumptions
Assumptions Register
Every hard-coded number used anywhere in the analysis — cite here, reference from notebooks via hwi.config
Parameter | Value | Rationale | Source | Used in
Service level z | 1.65 | 95 % cycle service level — standard for A-class spares | docs/04_methodology.md | FC-03 safety stock
Holding cost rate | 0.18 | 18 % of unit cost per year (capital + storage + obsolescence) | Team assumption, industry norm 15–25 % | EOQ
Ordering cost per PO (₹) | 2500 | Admin + inspection cost per import PO | Team assumption | EOQ
Dead-stock threshold (days) | 180 | No OUT movement in 180 days | Team assumption | INV-07
Churn threshold (days) | 180 | No order in 180 days | Team assumption | CUS-04
ABC cut-offs | 80 % / 95 % | Cumulative revenue share | Pareto convention | INV-08
XYZ cut-offs (CV) | 0.5 / 1.0 | Coefficient of variation of monthly demand | Standard | Classification
Forecast test window | 2024 | Train 2019–2023, test 2024 | Team decision, Week 1 | FC-01
Analysis as-of date | 31-Jan-2025 | Last ledger date + margin | Data coverage | Recency, ageing
Currency / units | INR, units per uom | All money in ₹; large values reported in ₹ Cr (1 Cr = 10,000,000) | Dataset | All